## Read Me
Grant Closeout Checklist
Final reports, expense reconciliation, outcome evidence, archived records, lessons learned and the renewal decision, in one workbook. Type the grant end date and the final report due date once, and every due date in the checklist and the timeline follows.
Version 1.0 ¦ October 2026 ¦ Published by GrantCue ¦ Free to copy, edit and share
Read this first
Illustrative figures, not data from a real organization. The two awards on the Award Status tab are composites built to show the formulas working. Delete them when you add your own.
This workbook is a planning tool, not legal or accounting advice. The award agreement and the funder's instructions decide the reports, the deadlines, the treatment of unspent funds and how long records are kept. There is no universal closeout deadline: adjust the timeline to the award terms.
Type only in the cream cells. The blue cells are formulas.
What is in this workbook
Closeout Checklist. One award, every closeout task in order: confirm the requirements, reconcile expenses, document outcomes, draft and submit the final report, archive the records, capture lessons learned, decide on renewal and run the quality review. Each row has an owner, a due date, a status and a place to note where the evidence is saved.
Closeout Timeline. The seven-step timeline with its dates calculated from the grant end date and the final report due date.
Final Report. The elements most final reports need, a table that connects each proposal promise to its closeout evidence, and the internal note to send once the report is in.
Award Status. One row per award across your portfolio, so you can see which grants are truly complete rather than just ended.
How closeout works
Start at least 60 days before the grant end date when possible; complex awards may need longer. Work in this order: review the award agreement and reporting instructions; confirm the end date and the final report due date; stop or separate expenses that fall outside the approved period; reconcile expenses to the approved budget; confirm match and in-kind documentation; gather outcome data and evidence; draft the narrative; draft the financial report or invoice; review with program and finance; submit through the official funder process; save the confirmation; archive and record the retention date; decide on renewal. If one step is blocked, the team can see exactly what is missing.
Closeout is not one person's job unless that person holds all the program and financial information. Program owns activities, outputs, outcomes and participant data. Finance owns final expenses, match and budget reconciliation. Grants owns the final report, funder communication and records. Leadership owns the renewal decision and relationship follow-up.
Use the original proposal as the outline of the final report and report against what was promised. If the project changed, explain why and whether the funder approved the change.
Risks and how to prevent them
Missing outcome data: track outcomes during the grant. Budget mismatch: reconcile monthly. Late report: add the closeout date early. Lost records: save files throughout the award. No renewal plan: discuss renewal before closeout.
Record retention
For federal awards, 2 CFR 200.334 generally requires records to be kept for three years from the date the final financial report is submitted, unless a longer period or an exception applies. Private funders may set their own rules. When unsure, ask finance or compliance before setting a retention date or deleting records.
Free to use, copy and share. No attribution required, though a link is always welcome.
More templates, worked examples and grant management tools: grantcue.com/blog
Source: https://www.grantcue.com/blog/grant-closeout-checklist ¦ GrantCue

## Closeout Checklist
Closeout Checklist
One checklist per award. Type the grant name, funder and dates in rows 4 to 8; the blue due dates fill in from them. Rows marked "After submission" take a date you type. Close the record only when every row is Done or Not applicable.
Grant name |  |  |  |  | Rows done
Funder |  |  |  |  | Rows still open
Grant end date |  |  |  |  | Days to final report due
Final report due date |  |  |  |  | Ready to close the record?
Due time, time zone and portal
Area | Task | When | Owner | Due | Status | Done on | Notes or where saved
Section 1. Confirm the closeout requirements
Requirements | Final report due date, time, time zone and portal confirmed from the award agreement | 60 days before end | Grants |  | Not started
Requirements | Financial report format and required detail confirmed | 60 days before end | Finance |  | Not started
Requirements | Narrative report questions and word limits confirmed | 60 days before end | Grants |  | Not started
Requirements | Required attachments listed: receipts, photos, data, certifications | 60 days before end | Grants |  | Not started
Requirements | Rule for unspent funds confirmed: return or carryover | 60 days before end | Finance |  | Not started
Requirements | Record retention period confirmed | 60 days before end | Grants |  | Not started
Requirements | Final report due date added to the grant calendar | 60 days before end | Grants |  | Not started
Requirements | Spending and outcomes reviewed against the award | 60 days before end | Finance |  | Not started
Section 2. Reconcile expenses
Expenses | Expenses that fall outside the approved period stopped or separated | 45 days before end | Finance |  | Not started
Expenses | Total award amount, payments received, expenses charged and remaining balance reconciled | 15 days before due | Finance |  | Not started
Expenses | Match or cost share reconciled, and required match documented | 15 days before due | Finance |  | Not started
Expenses | Indirect costs reconciled | 15 days before due | Finance |  | Not started
Expenses | Budget modifications reconciled, and approvals stored with the award | 15 days before due | Finance |  | Not started
Expenses | Unallowable expenses removed | 15 days before due | Finance |  | Not started
Expenses | Final expense total matches the ledger | 15 days before due | Finance |  | Not started
Expenses | Costs fall within the project and budget period | 15 days before due | Finance |  | Not started
Expenses | Restricted categories were followed | 15 days before due | Finance |  | Not started
Expenses | Payroll, contractor, travel, supply and indirect cost support saved | 15 days before due | Finance |  | Not started
Expenses | Unspent funds handled according to funder instructions | 15 days before due | Finance |  | Not started
Expenses | Final invoice or reimbursement request matches the report | 15 days before due | Finance |  | Not started
Expenses | Any difference from the approved budget explained, and funder approval confirmed where needed | 15 days before due | Finance |  | Not started
Expenses | Program staff confirmed the reported expenses make sense given the activities in the narrative | 15 days before due | Program |  | Not started
Section 3. Document outcomes
Outcomes | Missing outcome data and documents identified | 45 days before end | Program |  | Not started
Outcomes | Participants served: counts and demographics | 45 days before end | Program |  | Not started
Outcomes | Services delivered: activity logs | 45 days before end | Program |  | Not started
Outcomes | Outcomes achieved: survey, assessment or program data | 45 days before end | Program |  | Not started
Outcomes | Partnerships: partner records or letters | 45 days before end | Program |  | Not started
Outcomes | Community impact: stories, data and examples | 45 days before end | Program |  | Not started
Section 4. Draft, review and submit the final report
Final report | Final report outline drafted from the original proposal | 30 days before end | Grants |  | Not started
Final report | Final narrative report drafted | 15 days before due | Grants |  | Not started
Final report | Final financial report or invoice drafted | 15 days before due | Finance |  | Not started
Final report | Report reviewed with program and finance | 7 days before due | Grants |  | Not started
Final report | Submitted through the official funder process | Due date | Grants |  | Not started
Final report | Confirmation saved: portal confirmation, email receipt, uploaded files, final expense total, submission date and who submitted | Due date | Grants |  | Not started
Section 5. Archive records
Records | Original proposal saved | After submission | Grants |  | Not started
Records | Award letter and grant agreement saved | After submission | Grants |  | Not started
Records | Approved budget and budget modifications saved | After submission | Finance |  | Not started
Records | All reports saved | After submission | Grants |  | Not started
Records | Receipts and invoices saved | After submission | Finance |  | Not started
Records | Funder communications saved | After submission | Grants |  | Not started
Records | Final confirmation and closeout notes saved | After submission | Grants |  | Not started
Records | File names consistent, for example: Final Report Submitted 2026-10-30, Final Budget Reconciliation, Award Letter, Approved Budget, Funder Confirmation, Lessons Learned | After submission | Grants |  | Not started
Records | Retention date recorded on the Award Status tab | After submission | Grants |  | Not started
Section 6. Capture lessons learned
Lessons | Did the project deliver what was promised? | After submission | All |  | Not started
Lessons | Was the budget realistic? | After submission | All |  | Not started
Lessons | Were reporting requirements manageable? | After submission | All |  | Not started
Lessons | Did the funder relationship strengthen? | After submission | All |  | Not started
Lessons | What should change next time? | After submission | All |  | Not started
Section 7. Decide on renewal
Renewal | Renewal discussion held: fit with funder priorities, strength of outcomes, administrative effort, funder communication, a logical next phase, what to change | After submission | Leadership |  | Not started
Renewal | Renewal decision saved in the grant record | After submission | Leadership |  | Not started
Renewal | If reapplying: future opportunity created with the expected cycle, likely request amount and content to reuse | After submission | Grants |  | Not started
Renewal | If not reapplying: the reason documented | After submission | Leadership |  | Not started
Renewal | Outcome summaries, budget notes and funder feedback saved to the proposal library | After submission | Grants |  | Not started
Renewal | Internal closeout note sent (text on the Final Report tab) | After submission | Grants |  | Not started
Section 8. Quality review before you close the record
Quality review | The final report answers the funder's questions | After submission | Grants |  | Not started
Quality review | Financial totals match finance records | After submission | Finance |  | Not started
Quality review | Outcomes are supported by data | After submission | Program |  | Not started
Quality review | Communications are saved | After submission | Grants |  | Not started
Quality review | The renewal decision is recorded | After submission | Leadership |  | Not started
Quality review | Retention rules are understood | After submission | Grants |  | Not started
Do not close the record just because the project ended. Close it when reporting, reconciliation, archiving and renewal review are all complete.

## Closeout Timeline
Closeout Timeline
Dates come from the grant end date and the final report due date on the Closeout Checklist tab. Start at least 60 days before the end date when possible; complex awards may need a longer timeline.
Timing | Task | Date | Owner | Status
60 days before end | Review spending, outcomes and report requirements |  | Grants
45 days before end | Identify missing data and documents |  | Program
30 days before end | Draft the final report outline |  | Grants
15 days before due | Reconcile final expenses |  | Finance
7 days before due | Final internal review |  | Grants
Due date | Submit the final report |  | Grants
After submission | Save the confirmation and archive the records |  | Grants

## Final Report
Final Report
Most final reports need the same core elements, even when the funder uses its own form. Use the original proposal as the outline and report against what was promised.
Element | What to include | Evidence or source | Status
Project summary | What was funded, in two or three sentences
Original goals | The goals and objectives exactly as the proposal stated them
Activities completed | What happened, with counts
People or communities served | Counts and demographics
Outcomes achieved | Results against each objective, with the data behind them
Differences between the plan and reality | What changed, why, and whether the funder approved it
How funds were spent | Final expenses against the approved budget
Lessons learned | What the team would keep and change
Partner contributions | What each partner delivered
Sustainability or next steps | What continues, and how it is funded
Proposal promise and closeout evidence
Proposal promise | What the proposal said | What happened, and the evidence | Where it is saved
Participants served
Services delivered
Outcomes achieved
Partnerships
Community impact
Internal closeout note
The final report for [Grant Name] was submitted on [date]. Final expenses totaled [amount], and the project achieved [brief outcome]. Confirmation and supporting documents are saved in [location]. The team recommends [renewal / no renewal / follow-up] based on [reason].

## Award Status
Award Status
Illustrative figures, not data from a real organization. One row per award, so you can see which grants are complete rather than just ended. The federal default retention date is three years after the final financial report is submitted; a longer period or an exception may apply, and private funders set their own rules.
Grant name | Grant end date | Final report due | Program data status | Finance reconciliation status | Final report status | Confirmation saved | Renewal decision | Final financial report submitted | Federal default retention date | Record closed?
Example Arts Access Grant (composite) | 2026-06-30 | 2026-08-29 | Complete | Complete | Submitted | Yes | Reapply | 2026-08-20
Example Youth Mentoring Grant (composite) | 2026-09-30 | 2026-12-29 | In progress | Not started | Drafting | No | Not decided
Formulas:
Federal default retention date = IF([Final financial report submitted]="","",EDATE([Final financial report submitted],36))