## Read Me
Grant Proposal Timeline: Worked Example
The project timeline and the writing schedule for one fictional application: the Family Attendance Coaching Project, a 12-month request of $125,840 from Sedgewater Family Network to the Corwin Lake Community Foundation's Early Grades Fund.
Worked example 1.0 ¦ October 2026 ¦ Published by GrantCue ¦ Free to copy, edit and share
Read this first
Fictional example, not data from a real organization. Sedgewater Family Network, its schools, the funder and every figure are invented to show the file working. The project runs one 12-month budget period (project months 1 to 12, July 2027 to June 2028), so no row crosses a budget period. The deadline on the Writing Timeline tab is the Foundation's full-proposal deadline in this example, and a foundation portal does not use SAM.gov or Grants.gov, so those two dates are marked as not needed. The same project appears in GrantCue's worked examples of a budget, statement of need, logic model, evaluation plan, letter of intent and full proposal.
This workbook is a starting point to adapt, not legal or accounting advice. The notice of funding opportunity and the award terms decide the period of performance, the budget periods, the due dates and the reports that apply to you.
Type only in the cream cells. The blue cells are formulas: if you type over one, the file stops calculating that row.
What is in this workbook
Project Timeline. One row per funded activity: activity, start month, end month, responsible role, deliverable, and the evaluation data it produces. Formulas show which budget period each row falls in, flag rows that cross a budget-period boundary or end after the period of performance, and turn project months into calendar dates for your internal calendar once you type an award start date.
Quarter View. The same rows as a Gantt-style table built by formulas: a square marks each quarter an activity runs, a diamond marks the quarter its deliverable is due. Up to 20 quarters (60 months).
Writing Timeline. The 8-week schedule from the article, counted back from the deadline you type, with an internal due date and a status for every week, plus the dates registration and validation force on you.
Two-Week Sprint. The compressed schedule for an opportunity found late, dated from the same deadline.
Timeline Checks. The checks that catch a timeline that contradicts the budget, the evaluation plan or the reporting schedule. Some are calculated; the rest you confirm by hand.
Rules the project timeline has to respect
Use project months, not calendar dates. The award start moves, so write Month 1, never January 2027. The calendar-date columns are for your own calendar after the award notice arrives, not for the proposal.
A budget period and the period of performance are different spans. Under 2 CFR 200.1, a budget period is the time interval from the start date of a funded portion of an award to the end date of that funded portion, during which recipients and subrecipients are authorized to incur financial obligations; the period of performance runs between the award's start and end dates and may include one or more budget periods. Award notices state both (2 CFR 200.211(b)(5) and (b)(6)).
Costs other than administrative closeout costs must be incurred during the approved budget period (2 CFR 200.403(h)). An activity in month 14 staffed by a position funded only through month 12 is the contradiction a reviewer catches.
Build the timeline after the budget, and use the same nouns as the budget, the evaluation plan and the logic model, so a reviewer moving between pages never has to translate.
Dates the writing schedule cannot move
Grants.gov says you can't start applying until your organization is registered in SAM.gov, and to allow up to 10 business days for SAM registration to become active (Grants.gov, applicant registration, read October 6, 2026).
A Grants.gov submission produces a receipt email, then a validation confirmation or a rejection with errors. If no email arrives within two business days, Grants.gov says to check your spam folder and then contact support (Grants.gov, check application status, read October 6, 2026). A rejection that lands after the closing time means the deadline is missed.
The closing hour matters as much as the date. NIH states that applications are due by 5:00 PM local time of the applicant organization on the due date (NIH standard due dates, read October 6, 2026). Type the closing time from your own notice.
The business-day formulas (WORKDAY) skip Saturdays and Sundays only. Move a date by hand when a holiday falls inside it.
Reuse notes
Save a clean copy as the master. For each opportunity, copy it, type the deadline and the period of performance, and keep the copy with the opportunity record. A timeline living in somebody's inbox disappears the week they take leave.
Free to use, copy and share. No attribution required, though a link is always welcome.
More templates, worked examples and grant management tools: grantcue.com/blog
Source: https://www.grantcue.com/blog/grant-proposal-timeline-example-template ¦ GrantCue

## Project Timeline
Project Timeline
Fictional example, not data from a real organization. One row per funded activity, ordered by start month. Use project months (Month 1 is the award start). Type in the cream cells; the blue cells are formulas.
Project | Family Attendance Coaching Project, Sedgewater Family Network (fictional)
Period of performance (months) | 12
Budget period length (months) | 12
Award start date (optional, internal calendar only) | 2027-07-01
Activity | Start month | End month | Responsible role | Deliverable | Evaluation data collected | Budget period | Crosses a budget period? | Within the period of performance? | Start date (internal) | End date (internal)
Hire and train the second attendance coach | 1 | 2 | Program Manager | Second coach hired; both coaches trained in the coaching protocol and the barrier screen
Renew the data-sharing agreement and referral protocols | 1 | 2 | Executive Director | Signed 2027-28 data-sharing addendum; referral protocol with the county health clinic
Monthly identification of eligible students | 2 | 3 | Program Manager | Eligibility list for both schools from 2026-27 attendance records | 2026-27 days absent for each eligible student (baseline)
Outreach, intake and barrier screens | 2 | 5 | Attendance Coaches | 120 students enrolled and screened by November 15 | Intake barrier screen
Tiered coaching and home visits | 3 | 12 | Attendance Coaches | At least 2,000 coaching contacts and 240 home visits logged | Coaching contacts and home visits, monthly from the case log
Ride vouchers and referrals | 3 | 12 | Attendance Coaches | 500 ride vouchers issued; referrals logged with completion dates | Voucher log; referral completions
Attendance team meetings at both schools | 3 | 11 | Program Manager | 36 meetings with action notes, 18 per school
Monthly attendance data review | 3 | 12 | Program Manager | 10 monthly attendance files for enrolled students | District attendance records, monthly
Family attendance nights | 4 | 10 | Program Manager | 4 family nights held; sign-in sheets saved | Sign-in sheets
District budget request for 2028-29 coaching | 6 | 11 | Executive Director | Budget request submitted in February; school board decision recorded in May
Midyear progress report to the Foundation | 7 | 7 | Program Manager | Midyear progress report submitted by January 31, 2028 | Midyear attendance analysis
Spring family survey | 10 | 11 | Evaluator | Survey dataset in English and Spanish, with the response rate | Spring family survey
End-of-year attendance analysis | 12 | 12 | Evaluator | Outcomes memo: share below the threshold, change in days absent, comparison with the district's other schools | Final 2027-28 attendance records
Final report preparation and financial reconciliation | 12 | 12 | Program Manager | Final narrative and financial report drafted; submitted to the Foundation by August 31, 2028, with no grant costs after June 30
Formulas:
Start date (internal) = IF(OR(B7="",[Start month]=""),"",EDATE(B7,[Start month]-1))
End date (internal) = IF(OR(B7="",[End month]=""),"",EDATE(B7,[End month])-1)

## Quarter View
Quarter View
Fictional example, not data from a real organization. Built from the Project Timeline tab: ■ means the activity runs in that quarter, ◆ means its deliverable is due in that quarter (the quarter of its end month). Quarters after the period of performance stay blank.
Activity | Q1 | Q2 | Q3 | Q4 | Q5 | Q6 | Q7 | Q8 | Q9 | Q10 | Q11 | Q12 | Q13 | Q14 | Q15 | Q16 | Q17 | Q18 | Q19 | Q20
Project months | 1 to 3 | 4 to 6 | 7 to 9 | 10 to 12 | 13 to 15 | 16 to 18 | 19 to 21 | 22 to 24 | 25 to 27 | 28 to 30 | 31 to 33 | 34 to 36 | 37 to 39 | 40 to 42 | 43 to 45 | 46 to 48 | 49 to 51 | 52 to 54 | 55 to 57 | 58 to 60

## Writing Timeline
Writing Timeline: 8 Weeks From the Deadline Backward
Fictional dates for the example application. Type the deadline; every internal due date moves with it. Each week's internal due date is the last business day before the next week starts; week 8 uses the target submission date.
Submission deadline (date) | 2027-04-16
Closing time on the deadline (from the notice) | 5:00 PM local time, from the Foundation's invitation to submit a full proposal
Submit this many business days early | 3 | The article's rule: submit at least 3 business days early
Target submission date
If SAM.gov is not active, start registration no later than |  | Not needed here: the Foundation's portal does not use SAM.gov. The date stays for federal applications.
No Grants.gov email by this date? Check spam, then contact support |  | The Foundation's portal sends a confirmation email on submission; if none arrives within two business days, call the program officer.
Week | Countdown | Component | Owner | Week starts | Internal due date | Status | Days from today
1 |  | Read the Foundation's invitation and guidelines end to end, confirm the invited amount and eligibility, build a requirement checklist | Development Director |  |  | Done
2 |  | Confirm the go decision, assign sections, set internal due dates, request letters of support from both principals, the county health clinic and the university | Development Director, Executive Director |  |  | Done
3 |  | Draft the statement of need, pull 2025-26 attendance data under the data-sharing agreement, draft activities and the project timeline | Program Manager |  |  | Done
4 |  | Draft goals, objectives and the evaluation plan with the university evaluator; build the budget and budget narrative | Program Manager, Finance Manager |  |  | Done
5 |  | Assemble the first full draft, check the timeline against the budget period, inventory attachments | Development Director |  |  | Done
6 |  | Review against the Foundation's review criteria, revise, chase missing letters | Executive Director, board grants committee |  |  | Done
7 |  | Final edits, formatting, page-limit check, signatures, upload a draft in the Foundation's portal | Development Director |  |  | Done
8 |  | Submit at least 3 business days early, confirm the portal's confirmation email | Development Director |  |  | Done
Registration and validation drive the last two weeks. Spare rows: type a week number from 1 to 8 and the dates fill in.
Formulas:
Internal due date = IF(OR([Week]="",B4=""),"",IF([Week]=8,B7,WORKDAY(B4-7*(8-[Week]),-1)))
Days from today = IF([Internal due date]="","",[Internal due date]-TODAY())

## Two-Week Sprint
Two-Week Sprint: Compressing When You Find the Opportunity Late
Fictional dates for the example application. Day 14 is the deadline on the Writing Timeline tab; the other days count back from it in calendar days. Cut the sequence, not the care in any single piece: budget before narrative, one reviewer, and the last day kept free for submission problems.
First day | Last day | Tasks | From | To | Owner | Status
1 | 1 | Read the notice, confirm eligibility, verify SAM.gov and portal registrations, go or no-go, send letter requests |  |  |  | Not started
2 | 2 | Lock scope on one page: need, population, activities, outcomes, request amount |  |  |  | Not started
3 | 4 | Finance builds the budget first, fixing the scope the narrative describes |  |  |  | Not started
5 | 5 | Build the project timeline from the budget lines |  |  |  | Not started
6 | 8 | Draft the narrative: need, approach, capacity, evaluation |  |  |  | Not started
9 | 9 | Assemble attachments, chase outstanding letters |  |  |  | Not started
10 | 10 | One reviewer reads the package against the scoring criteria |  |  |  | Not started
11 | 11 | Revise from that review only |  |  |  | Not started
12 | 12 | Format, page-limit check, signatures, final package |  |  |  | Not started
13 | 14 | Submit, then hold the last day for validation errors |  |  |  | Not started
Some things will not compress. SAM.gov registration can take up to 10 business days to become active, so a lapsed one ends a two-week sprint on day one. Signatures run on somebody else's calendar, so the request goes out on day 1 with a placeholder.
Not used for this application: the Foundation's invitation arrived on February 19, 2027, eight weeks before the deadline, so the team followed the Writing Timeline. The tab stays in the file as the fallback plan.

## Timeline Checks
Timeline Checks
Run these before the timeline goes into the proposal. Rows 5 to 11 are calculated from the Project Timeline tab; rows 12 and 13 you confirm by hand.
Check | What to compare | Result | Fix when it fails
Period length | Timeline end month equals the period of performance |  | Extend or trim rows so the timeline covers the whole period of performance
Inside the period | No row ends after the period of performance or has its months reversed |  | Activities after the period are not fundable; closeout is the only exception
Budget boundaries | Year-boundary activities sit on the correct side |  | Split the row at the boundary, or confirm the budget funds it in both periods
Reporting | Interim and final report dates are timeline rows |  | Put interim and final report dates on the timeline as work
Verifiable milestones | Every activity has a deliverable with a number or an artifact |  | Attach a number or an artifact to every milestone
Spread across the period | Deliverables are due in the second half, not only the first |  | Spread deliverables across all quarters
Evaluation timing | Data collection points appear in the evaluation plan |  | Add a data collection row per measure, with the same wording as the evaluation plan
Staffing | Each activity's owner is funded during those months | Yes | Build the timeline after the budget; move or re-fund rows whose owner is not funded
Same nouns | Row labels match the budget categories and the logic model activities | Yes | Rename rows so a reviewer never has to translate between pages