## Logic Model
Program Logic Model: Worked Example
Program: Family Attendance Coaching Project, Sedgewater Family Network Prepared: April 2027 Read left to right: if we have these, and do these, then…
Fictional example: the organization, schools, partners, funder and every figure are invented. Outcomes were written first, then the activities that would cause them, then the outputs and inputs; the inputs match the worked-example budget line by line.
Inputs | Activities | Outputs | Short-term Outcomes (1 yr) | Mid-term Outcomes (1–3 yrs) | Long-term Impact
Two attendance coaches, 0.75 FTE each, one based at each school | Monthly identification of eligible students from district attendance records | 120 students enrolled, 60 per school, by November 15, 2027 | 55 percent of enrolled students (66 of 120) finish 2027-28 missing fewer than 10 percent of enrolled days | Students who finished 2027-28 below the threshold stay below it in 2028-29, tracked under the data-sharing agreement | More students at Linnet Street and Ferrow Park read at grade level by the end of third grade
Program Manager, 0.15 FTE; Executive Director, 0.05 FTE (match) | Intake and 12-item barrier screen with each family, in English or Spanish | 120 barrier screens completed | Enrolled students miss an average of at least 5 fewer days than in 2026-27 | Both schools keep the attendance team routine and the written coaching protocol | Chronic absence in the early grades is treated across Sedgewater County as a shared responsibility of schools and community partners
$125,840 from the Corwin Lake Community Foundation and $9,600 in match | Tiered coaching: weekly contact for students missing the most days, every two weeks for the rest, with home visits | At least 2,000 coaching contacts and 240 home visits | 80 percent of families with a barrier at intake have at least one completed support or referral for it | K-3 chronic absence at the two schools falls from 31 percent toward the district rate of 20 percent
Data-sharing agreement with Sedgewater County Schools (signed August 2025, renewed each July) | Ride vouchers and referrals to the school nurse, the county health clinic and the housing help line | 500 ride vouchers issued; referrals logged with completion dates | 70 percent of responding families report their main barrier is smaller than at intake
Office space at both schools, donated by the district | Attendance team meetings every two weeks at each school | 36 attendance team meetings, 18 per school
Ride vouchers, interpretation, family attendance kits, two laptops | Four family attendance nights | 4 family nights, about 200 attendees in all; 150 kits distributed
Evaluation contract with the North Basin State University Center for Community Research | Monthly attendance data review and tier adjustments | 10 monthly attendance reviews
Assumptions: families take part voluntarily and consent to the coach seeing attendance; the district renews the data-sharing agreement each July; ride vouchers can be booked for trips before 7:30 a.m.; the barriers seen in the 2025-26 pilot (transportation, early work shifts, child health, housing) are also the main barriers at Ferrow Park.
External factors: district decisions on bus routes and the walk zone; flu and other illness seasons that raise absences across the district; family moves driven by local rents; the school board's 2028-29 budget decision on continuing coaching.