## Read Me
Post-Award Grant Management Checklist
Everything a team does between the award letter and closeout: award setup, restriction review, budget and outcome tracking, reports, funder communication and closeout preparation, for one award.
Version 1.0 ¦ October 2026 ¦ Published by GrantCue ¦ Free to copy, edit and share
Read this first
Make one copy of this workbook per award. Type only in the cream cells; the blue cells are formulas.
Start from the funder's official documents, not from the team's memory of the proposal: the award agreement, approved budget, approved scope of work, reporting schedule, allowable cost rules, match requirements, procurement rules if they apply, and any portal instructions. For federal and federal pass-through awards, also review the relevant 2 CFR Part 200 requirements and the specific award terms. This checklist is not a legal guide; check the authoritative source before making compliance decisions.
Most post-award problems begin when a team celebrates the win but never turns it into an operating plan. Hold the kickoff within one week of the award and convert every proposal promise into an operating task.
What is in this workbook
Award Summary. The award record from the official documents, the owners, a small dashboard (spent, remaining, percent of the award spent against percent of the period elapsed, the next report due) and the risk flags.
Checklist. Tasks by timeframe: the first week, the kickoff agenda, the restriction review, monthly and quarterly reviews, the workflow before each report, the steps when the project changes, and closeout preparation.
Data Plan. Each proposal promise turned into a data source, an owner and a collection frequency, so the report is not the first time anyone looks at the metrics.
Reports. Every report the award requires, with internal draft and review dates and the confirmation once it is submitted.
Monthly Review. The monthly meeting questions and a log of each meeting's action items, owners and dates.
Communications. A log of every important exchange with the funder, so the history survives staff changes.
Roles
Grant owner: coordinates reporting and funder communication. Program owner: delivers activities and outcome data. Finance owner: tracks spending and financial reports. Executive owner: approves major changes and funder commitments. Admin support: saves documents and confirmations. Post-award work fails when everyone assumes someone else is tracking the award.
File structure
Use these folders: Award agreement; Approved proposal; Approved budget; Reports; Finance documentation; Funder communications; Closeout. Keep final documents separate from drafts.
When to contact the funder
When the project scope changes, when spending will differ materially from the approved budget, when a report will be late, when key staff change, when you need clarification, or when the project reaches a notable milestone. Log each exchange on the Communications tab. Do not assume changes are allowed.
Common scenarios
Spending behind schedule: find out why (a hiring delay, a slow vendor contract, slow participation), compare it with the award terms and decide whether the funder needs an update. Spending ahead of schedule: finance checks that the costs are allowable and that the budget will cover later activities. Outcomes below target: document the cause and the correction plan. A staff change: run a handoff meeting covering the award summary, budget status, next report, open funder questions and file location.
Free to use, copy and share. No attribution required, though a link is always welcome.
More templates, worked examples and grant management tools: grantcue.com/blog
Source: https://www.grantcue.com/blog/post-award-grant-management-checklist ¦ GrantCue

## Award Summary
Award Summary
Fill this from the official documents. It gives program, finance and leadership one shared reading of the award. Kickoff and first-week due dates on the Checklist tab count from the award notice date in B8.
Field | Value | What to capture
Award name |  | The funder's official grant name
Award number |  | Contract, grant or agreement ID
Funder |  | Foundation or agency name
Award notice date |  | The date the award letter arrived (date)
Award amount |  | Total approved funding (money)
Project period start |  | Start date (date)
Project period end |  | End date (date)
Budget period |  | The spending period, if different from the project period
Payment schedule |  | Upfront, reimbursement or installments
Budget categories |  | For example personnel, supplies, travel, indirect
Allowable and unallowable costs |  | The cost categories that are allowed or disallowed
Match |  | Cash or in-kind match requirement
Indirect cost rules |  | Rate and base allowed
Budget modification rules |  | Which changes need the funder's written approval
Procurement rules |  | If applicable
Reports |  | List every report on the Reports tab
Documentation required |  | Receipts, timesheets, participant data or other proof
Outcomes promised |  | List every promise on the Data Plan tab
Record retention |  | Required storage period
Program officer |  | Name, email, phone
Funder finance contact |  | Name, email, phone
Documents location |  | Link to the award folder
Grant owner |  | Coordinates reporting and funder communication
Program owner |  | Delivers activities and outcome data
Finance owner |  | Tracks spending and financial reports
Executive owner |  | Approves major changes and funder commitments
Admin support |  | Saves documents and confirmations
Backup reviewer |  | Second reader of the official documents
Closeout notes |  | Final report, final invoice, archive and retention notes
Dashboard
Amount spent to date |  | From the accounting system, updated monthly
Remaining budget |  | Award amount less amount spent
Percent of award spent |  | Compare with the next row
Percent of project period elapsed |  | A large gap between these two rows is a reason to mark a spending flag below
Days left in the project period |  | Counts down to the end date
Next report due |  | The earliest funder due date on the Reports tab with no submitted date
Closeout preparation starts |  | Review final expenses, outcomes and report fields at least 30 to 60 days before the end
Risk status |  | Your overall reading after the monthly review
Risk flags: mark Yes to act before a report is due
Flag | Present? | What to do
Spending behind schedule |  | Find out why, compare with the award terms and decide whether the funder needs an update
Spending ahead of schedule |  | Finance checks the costs are allowable and the budget still covers later activities
Outcome data missing |  | Fix the source on the Data Plan tab now, not at report time
Outcomes below target |  | Document the cause and the correction plan for the next report
Report due soon |  | Start the "Before each report" steps on the Checklist tab
Budget change needed |  | Follow the "When the project changes" steps on the Checklist tab
Funder approval needed |  | Contact the funder and save the written approval
Staff change |  | Run a handoff meeting: award summary, budget status, next report, open funder questions, file location
Closeout approaching |  | Start the "Before closeout" steps, then the grant closeout checklist

## Checklist
Checklist
Tasks by timeframe. First-week and kickoff dates count from the award notice date; closeout preparation counts back 60 days from the project end. Type the other dates yourself. Repeat the monthly, quarterly and per-report rows each time by copying them below the table.
Timeframe | Task | Owner | Due | Status | Notes
First week
First week | Save the award letter and agreement | Admin support |  | Not started
First week | Record the award amount, grant period and restrictions on the Award Summary tab | Grant owner |  | Not started
First week | Add every report date to the grant calendar and the Reports tab | Grant owner |  | Not started
First week | Assign internal owners for grant, program and finance | Executive owner |  | Not started
First week | Confirm the budget categories with finance | Finance owner |  | Not started
First week | Translate the promised outcomes into tracking fields on the Data Plan tab | Program owner |  | Not started
First week | Store the funder contacts and communication rules | Grant owner |  | Not started
First week | Set up the file structure listed on the Read Me tab | Admin support |  | Not started
First week | Schedule the kickoff meeting and the monthly check-ins | Grant owner |  | Not started
Kickoff meeting (within one week of the award): grants, program, finance, and leadership if needed
Kickoff | Review the award letter | Grant owner |  | Not started
Kickoff | Confirm the award amount and grant period | Grant owner |  | Not started
Kickoff | Review the approved budget | Finance owner |  | Not started
Kickoff | Review the restrictions | Finance owner |  | Not started
Kickoff | Confirm the activities and outcomes promised | Program owner |  | Not started
Kickoff | Add the report dates | Grant owner |  | Not started
Kickoff | Assign owners | Executive owner |  | Not started
Kickoff | Confirm document storage | Admin support |  | Not started
Kickoff | Discuss renewal or relationship strategy | Executive owner |  | Not started
Restriction review (before spending begins)
Restrictions | Allowable costs | Finance owner |  | Not started
Restrictions | Unallowable costs | Finance owner |  | Not started
Restrictions | Match | Finance owner |  | Not started
Restrictions | Indirect cost rules | Finance owner |  | Not started
Restrictions | Payment schedule | Finance owner |  | Not started
Restrictions | Budget modification rules | Grant owner |  | Not started
Restrictions | Procurement rules, if applicable | Finance owner |  | Not started
Restrictions | Reporting format | Grant owner |  | Not started
Restrictions | Record retention | Grant owner |  | Not started
Monthly
Monthly | Review spending: how much is spent and remains, whether expenses are allowable and match the approved budget, whether match is documented | Finance owner |  | Not started
Monthly | Review activities against the schedule | Program owner |  | Not started
Monthly | Review outcomes in the format the funder expects | Program owner |  | Not started
Monthly | Review funder communications | Grant owner |  | Not started
Monthly | Hold the monthly meeting and log it on the Monthly Review tab | Grant owner |  | Not started
Quarterly
Quarterly | Compare progress with the proposal promises | Program owner |  | Not started
Quarterly | Identify budget changes | Finance owner |  | Not started
Quarterly | Prepare the upcoming reports | Grant owner |  | Not started
Quarterly | Discuss renewal or continuation | Executive owner |  | Not started
Before each report (set an internal draft deadline, an internal review deadline and a final submission deadline)
Each report | Review the funder's instructions | Grant owner |  | Not started
Each report | Gather program data | Program owner |  | Not started
Each report | Gather finance data | Finance owner |  | Not started
Each report | Draft the narrative | Grant owner |  | Not started
Each report | Reconcile the budget | Finance owner |  | Not started
Each report | Review internally | Executive owner |  | Not started
Each report | Submit | Grant owner |  | Not started
Each report | Save the confirmation | Admin support |  | Not started
When the project changes
Changes | Review the award terms | Grant owner |  | Not started
Changes | Document the proposed change | Program owner |  | Not started
Changes | Ask whether funder approval is required | Grant owner |  | Not started
Changes | Contact the funder if needed | Grant owner |  | Not started
Changes | Save the written approval | Admin support |  | Not started
Changes | Update the budget and work plan | Finance owner |  | Not started
Before closeout (at least 30 to 60 days before the grant ends)
Before closeout | Review final expenses | Finance owner |  | Not started
Before closeout | Review remaining funds | Finance owner |  | Not started
Before closeout | Review final outputs and outcomes | Program owner |  | Not started
Before closeout | Review the required final report fields | Grant owner |  | Not started
Before closeout | Review the required attachments | Grant owner |  | Not started
Before closeout | Review the record retention rules | Grant owner |  | Not started
Before closeout | Review the renewal opportunity | Executive owner |  | Not started
Before closeout | Start the grant closeout checklist | Grant owner |  | Not started

## Data Plan
Data Plan
Turn each proposal promise into a data plan so reporting is easier and more accurate. Track outcomes as the program runs, not at the end. The rows below are examples of the kinds of promises most awards carry; replace them with the promises in your proposal and type your targets.
Proposal promise | Tracking need | Data source | Owner | Frequency | Target | Latest value | As of | Notes
Number served | Participant count | Intake records | Program lead | Monthly
Service hours | Attendance or activity logs | Activity logs | Program lead | Monthly
Training delivered | Session records | Attendance logs | Site coordinator | Monthly
Improvement target | Assessment or survey | Survey or assessment | Evaluation owner | Midpoint and final
Partnership activity | Meeting notes and deliverables | Meeting notes | Program lead | Quarterly
Spending | Spending against the approved budget | Accounting records | Finance | Monthly

## Reports
Reports
One row per report the award agreement requires. Set an internal draft date and an internal review date ahead of each funder due date; for larger awards, start the draft weeks ahead. Days until due stops counting once a submitted date is typed.
Report | Type | Funder due date | Internal draft date | Internal review date | Format and portal | Owner | Submitted on | Confirmation saved | Days until due
Formulas:
Days until due = IF(OR([Funder due date]="",[Submitted on]<>""),"",[Funder due date]-TODAY())

## Monthly Review
Monthly Review
Meet monthly for each active award. End each meeting with action items, owners and dates. If there are none, record that the grant was reviewed and no issues were found: that note helps later when staff need to understand the award history.
Questions for every monthly meeting
1. Are expenses aligned with the approved budget?
2. Are any costs close to a restricted category?
3. Is the project on schedule?
4. Are outcomes being tracked in the format the funder expects?
5. Are match or in-kind contributions documented?
6. Are subrecipient, contractor or partner records complete?
7. Are upcoming reports visible on the calendar?
8. Does the funder need to approve any change?
9. Is closeout still on track?
Meeting date | Spent to date | Issues found (question numbers and what) | Action items | Owners | Due dates | Notes
|  | None | None |  |  | Reviewed, no issues found

## Communications
Communications
Store every important funder communication so the history survives if a staff member leaves: award notices, clarifications, budget modification approvals, reporting guidance, site visit notes and renewal conversations.
Date | Type | Summary | Funder contact | Our contact | Saved at