# Research Grant Proposal Template

A research proposal is a bundle of separately formatted components, each with format rules set by the sponsor. This planner takes the component view: what each piece has to do, where its format comes from, who owns it and when it is due.

How to use this template: open the current solicitation or sponsor guide first. Fill in the component table from it, then work through each component's prompts. Format every component from the current sponsor guide, never from a colleague's old funded application: biosketch formats, data-sharing rules and page limits change, and the solicitation always overrides any template, including this one. Delete the instruction lines when you are done.

# Opportunity and deadlines

Sponsor and program: [sponsor, program, solicitation or notice number]

Sponsor deadline: [date and closing time]

Internal deadline (your sponsored programs office): [date; often several business days before the sponsor's]

Limited submission or internal clearance needed: [yes or no; status]

Review criteria, in the sponsor's words: [for NIH research project grants, Importance of the Research, Rigor and Feasibility, Expertise and Resources; for NSF, intellectual merit and broader impacts; or the sponsor's own list]

# Component table

List every component the solicitation requires, in its order. Most federal research applications have the eight below; add or remove rows to match yours.

| Component | Sponsor's name for it | Page or word limit | Format source (guide and section) | Owner | Draft due | Status |
| --- | --- | --- | --- | --- | --- | --- |
| Project summary or abstract |  |  |  |  |  |  |
| Specific aims or objectives |  |  |  |  |  |  |
| Research strategy or project description |  |  |  |  |  |  |
| Biosketches |  |  |  |  |  |  |
| Budget and justification |  |  |  |  |  |  |
| Data management or sharing plan |  |  |  |  |  |  |
| Facilities and resources |  |  |  |  |  |  |
| Letters of support or collaboration |  |  |  |  |  |  |
| [Other required component] |  |  |  |  |  |  |

# 1. Project Summary or Abstract

Follow the sponsor's length and required elements exactly; the summary is often the first thing every reviewer reads.

[Summary text, written after the aims and strategy are settled.]

# 2. Specific Aims or Objectives

The aims page carries the argument in miniature: an opening paragraph establishing the problem and the gap, a paragraph stating the central hypothesis and approach, then two to four aims, each one sentence of what plus one or two sentences of how and expected outcome. Aims should be independent: if Aim 2 collapses when Aim 1's hypothesis fails, a reviewer will see the risk. Use the one-page Specific Aims template for the full layout.

Problem and gap: [What is known, what is not, and why the gap matters.]

Central hypothesis and approach: [Hypothesis; overall approach.]

Aim 1: [What.] [How, and expected outcome.]

Aim 2: [What.] [How, and expected outcome.]

Aim 3: [What.] [How, and expected outcome.]

Independence check: [If Aim 1's hypothesis is not supported, what Aims 2 and 3 still deliver.]

# 3. Significance or Need

Prove a gap in knowledge the way a nonprofit proposal proves a community need: with citations and data, not adjectives. State what is known, what is not, and why the gap matters, using literature and preliminary data in place of community statistics.

What is known: [findings, with sources]

What is not known: [the gap]

Why it matters: [consequence of leaving the gap open]

Preliminary data: [your own results, if any]

# 4. Research Strategy or Project Description

Use the headings and order the sponsor gives. For example, NIH's Research Strategy uses Significance, Innovation and Approach, in that order. Even without an evaluation section, the approach has to answer how you will know it worked: milestones, decision points between aims and pre-specified analysis plans.

Required headings, in order: [from the sponsor's guide]

Approach for each aim: [design, sample, measures, analysis]

Milestones: [milestone, and the month it is due]

Decision points between aims: [what result leads to which next step]

Pre-specified analysis plan: [primary analysis for each aim]

Risks and alternatives: [what could fail, and what you would do]

# 5. Biosketches

Request biosketches early, in the sponsor's current format, from every person the sponsor requires.

| Person and role | Format required | Requested on | Received | Checked against current format |
| --- | --- | --- | --- | --- |

# 6. Budget and Justification

The line-item and justification mechanics are the same as any grant budget: show the math on every line. Research budgets add three things generic templates miss. Involve your grants office early.

Effort, in person-months, for each investigator, consistent with institutional commitments: [name or role, person-months per year]

Facilities and administrative (indirect) costs at the institution's negotiated rate: [rate, base, agreement date]

Sponsor-specific caps and exclusions: [salary caps, equipment thresholds, participant-support rules]

Subawards: [partner, amount, budget and justification requested on date]

# 7. Data Management or Sharing Plan

Where the sponsor requires one, answer four things concretely. Keep personal information out of anything that becomes public.

What data you will generate: [types and volume]

Formats and standards: [file formats, metadata, standards]

Where and when it will be shared: [repository, timing]

Who oversees compliance: [role]

# 8. Facilities and Resources

Describe the space, equipment and institutional support the project will use, in the sponsor's format.

[Facilities, equipment and other resources available to the project.]

# 9. Letters of Support or Collaboration

Send only the letters the solicitation authorizes, in the form it names. NSF expects letters of collaboration that state only the intent to collaborate; NIH has announced letters of collaboration in place of letters of support with Forms J.

| Writer | Role | Form required (support or collaboration) | Requested on | Received |
| --- | --- | --- | --- | --- |

# Timeline, counted back from the sponsor's deadline

About three months from fit check to submission. Shift every date earlier by your institution's internal deadline. Compressing this into three weeks is possible, and it is where formatting errors, budget mismatches and missed attachments come from.

| Weeks before deadline | What should be happening | Date | Owner | Done |
| --- | --- | --- | --- | --- |
| 12 or more | Opportunity identified and fit-checked; internal or limited-submission clearance confirmed |  |  |  |
| 10 | Specific aims drafted and circulated to collaborators |  |  |  |
| 8 | Research strategy in full draft; subawards and letters requested |  |  |  |
| 6 | Budget built with the grants office; biosketches requested in current format |  |  |  |
| 4 | Data management plan, facilities and supplementary documents complete |  |  |  |
| 2 | Full internal review against the sponsor's review criteria |  |  |  |
| 1 | Institutional sign-off; submission to the sponsor portal |  |  |  |
| After the deadline | Log the outcome; on award, put every report date on the calendar |  |  |  |

# Before it goes to the sponsored programs office

[ ] Every component in the table is drafted, in the format the current sponsor guide sets.

[ ] The budget, the effort in person-months and the strategy describe the same work.

[ ] Each aim can stand if another aim's hypothesis fails.

[ ] Biosketches are in the current format.

[ ] Only the letters the solicitation authorizes are included, in the form it names.

[ ] The package reaches the sponsored programs office by the internal deadline.

Source: https://www.grantcue.com/blog/research-grant-proposal-template-examples